## Overview
Approach & Use of the Action Tracker
Used to track all issues/risks/tasks (see definitions) that could impact a commitment from any meeting across working groups and steering group meetings. To use this spreadsheet, go to File> Make a Copy.
Definitions:
Issues | Have occurred and may impact existing milestones completion dates/budget
Risks | May occur and impact existing milestones, completion dates/budget
Tasks | Additional unplanned work identified which will impact existing milestones completion dates/budget
Legend - Impact
1 | Negligible: No effect on milestone dates; handled within normal workflow.
2 | Minor: Slight delay (< 2 days); absorbed by internal schedule buffers.
3 | Moderate: Milestone date at risk; requires shifting "All Hands" resources to recover.
4 | Major: Committed milestone missed; specific deliverables must be descoped to recover.
5 | Critical: Project failure imminent; requires immediate intervention from Faculty/Sponsor or significant scope pivot.
Legend - Status
0% | identified and unassigned
25% | identified and assigned
50% | in process
75% | near completion
100% | complete

## Issue-Risk-Task Tracker
# | Risk Category/Impacted Milestone | Risk Description | Impact | Mitigation Strategy | Primary Owner | Support | Type | Date Open | Target Date Close | Actual Date Close | % Complete | Notes
1 | Model Development | Int8 quantization may degrade accuracy below acceptable threshold (F1 < 0.60) | 2 | Test multiple quantization strategies (symmetric, asymmetric); fall back to int16 for critical layers | Che Li | Owen Wang | Risk | 2/11/2026 | 3/18/2026 |  | 0.25 | Identified during planning. Will validate after model training.
2 | RTL Design | Model may not fit in Basys 3 BRAM (225 KB) after adding control logic overhead | 4 | Keep model under 50% BRAM to leave headroom; behavioral simulation will estimate total usage | Owen Wang | Che Li | Risk | 2/11/2026 | 4/15/2026 |  | 0.25 | Initial estimate: ~47 KB for weights. Need to verify with full design.
3 | RTL Design | Timing closure failure at 100 MHz on XC7A35T | 3 | Design with conservative clock target (50-75 MHz); optimize critical path if needed | Owen Wang | Che Li | Risk | 2/11/2026 | 5/6/2026 |  | 0 | Will not be testable until synthesis phase.
4 | Verification | RTL simulation results may not match behavioral Python simulation | 3 | Use Python golden model outputs for layer-by-layer comparison in testbench | Che Li | Owen Wang | Risk | 2/11/2026 | 4/22/2026 |  | 0 | Mitigation planned. Will execute during verification phase.
5 | Synthesis & Demo | Vivado synthesis may exceed available LUTs or flip-flops for control logic | 3 | Simplify FSM; share resources between layers; estimate LUT usage early | Owen Wang | Che Li | Risk | 2/11/2026 | 5/6/2026 |  | 0 | 20,800 LUTs available. Will need synthesis to confirm.
6 | Model Development | MobileNetV2 (original candidate) is 15x too large for Basys 3 BRAM | 5 | Need to design a custom tiny CNN from scratch instead of using off-the-shelf model | Che Li | Owen Wang | Issue | 2/11/2026 | 2/25/2026 |  | 0.25 | Identified in week 1. Researching alternative architectures.
7 | Research & Planning | Survey existing FPGA CNN accelerator designs for reference | 1 | Review FINN framework documentation and academic papers | Che Li | Owen Wang | Task | 2/11/2026 | 2/25/2026 |  | 0.25 | Started this week.
8 | Research & Planning | Document Basys 3 resource limits (BRAM, DSP, LUT, FF, clock) | 1 | Read XC7A35T datasheet and compile resource table | Owen Wang | Che Li | Task | 2/11/2026 | 2/18/2026 |  | 0.5 | In progress.
9 | RTL Design | Implement MAC unit in SystemVerilog (int8 inputs, int32 accumulator) | 2 | Use existing mac_uint8_int32.sv as starting point | Owen Wang | Che Li | Task | 2/18/2026 | 3/18/2026 |  | 0 | Not started. Scheduled for week 4.
10 | RTL Design | Design weight BRAM controller for sequential layer loading | 3 | Store all weights in BRAM at init; use address offsets per layer | Owen Wang | Che Li | Task | 3/4/2026 | 4/1/2026 |  | 0 | Not started. Depends on model finalization.
11 | Verification | Create testbench comparing RTL output vs Python golden model per layer | 2 | Export Python int8 intermediate tensors as hex files for Verilog $readmemh | Che Li | Owen Wang | Task | 3/18/2026 | 4/15/2026 |  | 0 | Not started. Depends on behavioral sim completion.
12 | Synthesis & Demo | Prepare demo: classify sample images on FPGA and display result | 2 | Pre-load test images via UART; display class on 7-segment display | Che Li | Owen Wang | Task | 4/22/2026 | 5/6/2026 |  | 0 | Not started. Final phase.
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115