## Overview
Approach & Use of the Milestone Tracker
The Milestone Tracker is used to outline and prioritize the deliverables of the project. You can assign responsibility to individual team members for preparing and presenting individual aspects of the project, and keep track of who in the sponsor’s organization needs to sign off on something (usually not the sponsor). Faculty advisors will use the milestone tracker to determine your grade for participation in your team. While you can share it with the project sponsor, its main purpose is to provide a mechanism for internal review with student teams. To use this spreadsheet, go to File > Make a Copy.

## Template
MILESTONE TRACKER
Project Name | CNN CIFAR-10 Accelerator on Basys 3 FPGA |  | Legend | C | Complete
Project Sponsor | N/A |  |  | S | Started
Faculty Advisor | Ramesh Karri, Weihua Xiao |  |  | NS | Not Started
|  |  | Month | FEB |  |  | MAR |  |  |  | APR |  |  |  |  | MAY
|  |  | Wednesday's Date | 11 | 18 | 25 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13
|  |  | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Project Category | Milestone | Primary Owner | Support
Research & Planning | review: FPGA CNN accelerators | Che Li | Owen Wang | bar: FEB 11
Research & Planning | Select target model architecture | Owen Wang | Che Li | bar: FEB 11
Research & Planning | Basys 3 resource constraints analysis | Che Li | Owen Wang | bar: FEB 11 to FEB 18
Model Development | Design tiny CNN architecture (~48K params) | Che Li | Owen Wang | bar: FEB 18 to FEB 25
Model Development | Train CNN on CIFAR-10 (F1 >= 0.70) | Che Li | Owen Wang | bar: FEB 25 to MAR 4
Model Development | Export to ONNX (float32 + int8 quantized) | Che Li | Owen Wang | bar: MAR 4
Model Development | Verify int8 accuracy (minimal quantization loss) | Owen Wang | Che Li | bar: MAR 4 to MAR 11
FPGA Simulation | Build behavioral FPGA simulator (int8 arithmetic) | Che Li | Owen Wang | bar: MAR 11 to MAR 18
FPGA Simulation | Clock cycle & throughput analysis | Che Li | Owen Wang | bar: MAR 18
FPGA Simulation | BRAM/DSP resource utilization report | Owen Wang | Che Li | bar: MAR 18 to MAR 25
RTL Design | Design MAC unit (int8 multiply-accumulate) | Owen Wang | Che Li | bar: MAR 18 to APR 1
RTL Design | Design convolution datapath | Owen Wang | Che Li | bar: MAR 25 to APR 8
RTL Design | Design FC layer datapath | Che Li | Owen Wang | bar: APR 1 to APR 8
RTL Design | Design control FSM & memory interface | Owen Wang | Che Li | bar: APR 8 to APR 15
RTL Design | Integrate full CNN pipeline in Verilog | Owen Wang | Che Li | bar: APR 15 to APR 22
Verification | Testbench: MAC unit verification | Che Li | Owen Wang | bar: APR 1 to APR 8
Verification | Testbench: layer-level verification | Che Li | Owen Wang | bar: APR 8 to APR 15
Verification | Full system RTL simulation | Che Li | Owen Wang | bar: APR 22 to APR 29
Synthesis & Demo | Vivado synthesis for XC7A35T | Owen Wang | Che Li | bar: APR 29 to MAY 6
Synthesis & Demo | Timing closure & resource report | Owen Wang | Che Li | bar: MAY 6
Synthesis & Demo | Final presentation preparation | Che Li | Owen Wang | bar: MAY 6 to MAY 13
Synthesis & Demo | Final report & documentation | Che Li | Owen Wang | bar: MAY 13